## 01_Project_Charter
Project Aion — Project Charter & Intake
Fill these in once; we’ll keep them updated as the single source of truth.
Field | Notes
Project vision (1–2 sentences) | Aion Global (Equine & Sport) will be a 50/50 collaboration between me (Shane Clarke) and my business partner Ned Sangster to compile our collective knowledge and resources to create a next generation global thoroughbred racing trading & performance measurement ecosystem. 1) Strategic Intent Purpose: Develop Project Aion into a repeatable, auditable trading capability that can be (a) commercialised as a standalone business or (b) integrated into a partner fund structure with external bankroll. 2) Two Commercialisation Pathways Path A — New Business: Own capital (initially) + build track record + scale capital later Outputs: productised stack, operations, risk controls, reporting Path B — Fund Collaboration / Bankroll Partner: Partner supplies capital; you supply edge + system + execution Outputs: institutional-grade reporting, risk policy, model governance, controls, and a due diligence pack 3) A “Decision Gate” (make it explicit) Add a milestone like: Decision Gate (end of Q3 2026): Choose Path A or Path B based on: live/sim performance vs targets operational readiness (controls + reliability) partner appetite / pipeline legal + compliance feasibility
Primary objectives (top 5) | Consolidatie Database Platform, Advanced Proprietary Data Operation, Develop initial phase routine daily Hidden Merit manual trading list for France & Hong Kong, Develop Modelling & Automated Trading platforms (with Chatgpt assitance)
Non‑negotiable principles | Data Integrity, Precision, Flexibility, Adaptation
Scope: in / out
Target markets & instruments | France, Hong Kong, Japan, Australia, GCC
Time horizons (early/mid/late, pre‑race/in‑play, etc.)
Key resources (data, infra, tools, people) | Sri Lanka Video Analysts BPO - Proprietary Data Compilation, Aion Global Database System, Advanced ML Feature Library, XGBoost Modelling Platform, Automated Full Market Spectrum (Tote, Fixed Odds, Betfair Exchange, Asian Exchange , Fixed Odds)
Industry network / partnerships (optional)
Constraints (legal/compliance, latency, costs, etc.) | Phased development with development budget driven by trading revenue
Success metrics (KPIs)
Major risks & mitigations
Open questions / decisions needed

## 02_Roadmap
High‑Level Roadmap (Epics)
Baseline created: 2026-01-23 ¦ Adjust dates/owners freely.
Epic ID | Epic | Goal | Owner | Start | End | Duration (days) | Status | Dependency | Notes
E01 | Foundation & governance | Charter, structure, decision log, workflows | You | Q1_2026 | Q1_2026 | 15 | Not started |  | Sets up operating rhythm
E02 | Databases core | Fundamental/Technical/Transactional domains + schemas | TBD | Q1_2026 | Q2_2026 | 60 | Not started | E01
E03 | Feature system | Feature principles, profile, performance, ratings suite | TBD | Q1_2026 | Q2_2026 | 90 | Not started | E02 | POWRTG/SPDRTG/MRKRTG/TRKSPD/Time Standards
E04 | ML & MLOps | XGBoost module + MLflow + monitoring + gates | TBD | Q1_2026 | Q2_2026 | 90 | Not started | E03
E05 | Trading engines | OMS/execution/risk guardrails/sim | TBD | Q2_2026 | Q3_2026 | 90 | Not started | E02
E06 | Pulse & triggers | Race status, bet triggers, GUI pulse input | TBD | Q2_2026 | Q3_2026 | 90 | Not started | E02
E07 | Strategy library | Early/Mid/Late, Tote, Exchange, Fixed Odds, Dividend, cA, Staking | TBD | Q2_2026 | Q3_2026 | 90 | Not started | E05
E08 | GUI Glass Cockpit | Dash UI, design system, panels, icon library | TBD | Q2_2026 | Q3_2026 | 90 | Not started | E01
E09 | AWACS admin | Monitoring, kill switches, permissions, drills | TBD | Q3_2026 | Q3_2026 | 90 | Not started | E05
E10 | BI / Reporting / Recon | KPI layer, reporting packs, reconciliation controls | TBD | Q3_2026 | Q4_2026 | 120 | Not started | E02
E11 | Simulation & backtesting | Deterministic replay + exec sim + review packs | TBD | Q3_2026 | Q4_2026 | 120 | Not started | E03
E12 | IT Infrastructure | Envs, CI/CD, observability, security | TBD | Q1_2026 | Q4_2026 | 180 | Not started | E01 | Parallel stream

## 03_Gantt
Gantt Chart (High‑Level Epics)
Edit dates/status in 02_Roadmap. This sheet visualises automatically.
Epic ID | Epic | Owner | Start | End | Status | 2026-01-23 | 2026-01-30 | 2026-02-06 | 2026-02-13 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | 2026-07-17
|  |  | Q1_2026 | Q1_2026
|  |  | Q1_2026 | Q2_2026
|  |  | Q1_2026 | Q2_2026
|  |  | Q1_2026 | Q2_2026
|  |  | Q2_2026 | Q3_2026
|  |  | Q2_2026 | Q3_2026
|  |  | Q2_2026 | Q3_2026
|  |  | Q2_2026 | Q3_2026
|  |  | Q3_2026 | Q3_2026
|  |  | Q3_2026 | Q4_2026
|  |  | Q3_2026 | Q4_2026
|  |  | Q1_2026 | Q4_2026

## 04_Tickets
Ticketing System (Backlog)
Use this as a lightweight Jira: each row is a ticket. Filter/sort freely.
Ticket ID | Epic | Component | Type | Summary | Priority | Status | Owner | Estimate (hrs) | Start | Due | Dependencies | Acceptance Criteria | Created | Updated | Notes/Link | Realm | Framework_Path | Roadmap_Milestone
T-0001 | E01 | Project Foundation | Task | Finalize project charter + principles | P1 | In progress | You | 6 | 2026-01-23 | 2026-01-26 |  | Charter filled + agreed | 2026-01-23 | 2026-01-23 |  | 00_Triage_Inbox | Project_Aion/00_Triage_Inbox | TRIAGE
T-0002 | E02 | 07_Databases | Epic | Define canonical entity IDs + mappings | P1 | Not started | TBD | 12 | 2026-01-30 | 2026-02-13 | T-0001 | IDs documented + mapping rules | 2026-01-23 | 2026-01-23 |  | 00_Triage_Inbox | Project_Aion/00_Triage_Inbox | TRIAGE
T-0003 | E03 | Features_Profile | Task | Create feature spec template + catalog index | P1 | Not started | TBD | 8 | 2026-02-06 | 2026-02-20 | T-0001 | Template + example spec complete | 2026-01-23 | 2026-01-23 |  | 00_Triage_Inbox | Project_Aion/00_Triage_Inbox | TRIAGE
T-0004 | E08 | GUI_Glass_Cockpit | Task | Define cockpit screen map + key panels | P2 | Not started | TBD | 10 | 2026-02-13 | 2026-02-27 | T-0001 | Screen map + panel list | 2026-01-23 | 2026-01-23 |  | 00_Triage_Inbox | Project_Aion/00_Triage_Inbox | TRIAGE
T-0005 | E11 | Backtesting | Task | Decide replay granularity + event-time rules | P1 | Not started | TBD | 6 | 2026-02-13 | 2026-02-24 | T-0002 | Rules doc complete | 2026-01-23 | 2026-01-23 |  | 00_Triage_Inbox | Project_Aion/00_Triage_Inbox | TRIAGE

## 05_Dashboard
Dashboard (Auto)
Counts update as you add/edit tickets.
Ticket counts by Status |  |  | Ticket counts by Priority
Status | Count |  | Priority | Count
Backlog |  |  | P0
Not started |  |  | P1
In progress |  |  | P2
Blocked |  |  | P3
Ready for review
Done
Epics status snapshot
Epic | Status | Start | End

## 06_Decisions_Log
Decisions Log
Record key decisions so the project stays coherent over time.
Decision ID | Date | Decision | Rationale | Owner | Status | Impacted Components | Links/Notes